## Cleaned Data
Project ID | Client | Project Name | Project Manager | Region | Priority | Status | Budget | Actual Cost | Team Size | Completion (%) | Client Satisfaction | Start Date | End Date | Profit
PRJ0001 | Mtn Nigeria | Cybersecurity Upgrade | Sarah Musa | Abuja | Low | Completed | 120000000 | 55000000 | 5 | 90 | 5 | 2024-10-06 | 2025-03-13 | 65000000
PRJ0002 | Interswitch | Mobile Banking App | Grace Adeyemi | Port Harcourt | Medium | Completed | 120000000 | 100000000 | 20 | 50 | 1 |  |  | 20000000
PRJ0003 | Access Bank | Mobile Banking App | Grace Adeyemi | Lagos | Medium | Delayed | 60000000 | 100000000 | 0 | 0 | 1 |  |  | -40000000
PRJ0004 | Airtel | Ai Analytics Platform | John Iwoh | Kano | Medium | Completed | 15000000 | 55000000 | 20 | 90 | 1 |  |  | -40000000
PRJ0005 | Mtn Nigeria | Mobile Banking App | Sarah Musa | Abuja | Low | Delayed | 45000000 | 55000000 | 10 | 90 | 1 | 2024-06-16 |  | -10000000
PRJ0006 | Dangote Group | Cybersecurity Upgrade | Michael Dan | Lagos | Medium | In Progress | 25000000 | 20000000 | 20 | 100 | 3 | 2024-04-13 | 2024-06-13 | 5000000
PRJ0007 | Airtel | Cloud Infrastructure | David Bello | Abuja | Medium | Delayed | 120000000 | 100000000 | 5 | 25 | 4 |  |  | 20000000
PRJ0008 | Airtel | Erp Migration | John Iwoh | Lagos | Medium | Delayed | 60000000 | 35000000 | 10 | 0 | 3 |  | 2025-02-28 | 25000000
PRJ0009 | Dangote Group | Mobile Banking App | David Bello | Lagos | Medium | Delayed | 45000000 | 100000000 | 5 | 90 | 4 |  |  | -55000000
PRJ0010 | Flutterwave | Data Warehouse | Grace Adeyemi | Abuja | High | Delayed | 60000000 | 35000000 | 20 | 100 | 4 | 2025-02-04 | 2025-07-23 | 25000000
PRJ0011 | Dangote Group | Data Warehouse | John Iwoh | Abuja | High | In Progress | 25000000 | 100000000 | 10 | 25 | 1 |  |  | -75000000
PRJ0012 | Interswitch | Cybersecurity Upgrade | Sarah Musa | Abuja | Medium | Delayed | 15000000 | 20000000 | 20 | 75 | 5 |  |  | -5000000
PRJ0013 | Uba | Cloud Infrastructure | Michael Dan | Port Harcourt | Medium | In Progress | 15000000 | 100000000 | 0 | 90 | 4 | 2024-06-26 | 2024-10-01 | -85000000
PRJ0014 | Zenith Bank | Cloud Infrastructure | John Iwoh | Abuja | Medium | Completed | 15000000 | 20000000 | 15 | 50 | 5 |  | 2024-07-12 | -5000000
PRJ0015 | Nestle Nigeria | Ai Analytics Platform | Grace Adeyemi | Abuja | High | In Progress | 60000000 | 55000000 | 10 | 75 | 4 |  | 2025-04-15 | 5000000
PRJ0016 | Uba | Network Optimization | Sarah Musa | Abuja | Medium | In Progress | 25000000 | 20000000 | 10 | 75 | 3 |  |  | 5000000
PRJ0017 | Airtel | Erp Migration | Sarah Musa | Abuja | High | Delayed | 25000000 | 100000000 | 0 | 0 | 5 |  |  | -75000000
PRJ0018 | Dangote Group | Cybersecurity Upgrade | John Iwoh | Abuja | High | Delayed | 45000000 | 35000000 | 20 | 25 | 1 |  |  | 10000000
PRJ0019 | Nestle Nigeria | Cloud Infrastructure | Michael Dan | Kano | Medium | Completed | 25000000 | 100000000 | 10 | 100 | 2 | 2024-11-19 |  | -75000000
PRJ0020 | Nestle Nigeria | Mobile Banking App | David Bello | Abuja | Low | Completed | 25000000 | 12000000 | 0 | 25 | 3 | 2024-07-19 |  | 13000000
PRJ0021 | Flutterwave | Crm Implementation | Sarah Musa | Abuja | High | Delayed | 45000000 | 100000000 | 15 | 90 | 2 |  | 2025-06-07 | -55000000
PRJ0022 | Nestle Nigeria | Cybersecurity Upgrade | Grace Adeyemi | Lagos | High | Completed | 120000000 | 100000000 | 5 | 25 | 4 | 2024-09-01 |  | 20000000
PRJ0023 | Dangote Group | Network Optimization | Michael Dan | Kano | High | Delayed | 120000000 | 35000000 | 20 | 50 | 1 |  |  | 85000000
PRJ0024 | Mtn Nigeria | Network Optimization | John Iwoh | Lagos | High | Completed | 15000000 | 100000000 | 5 | 25 | 5 |  |  | -85000000
PRJ0025 | Dangote Group | Ai Analytics Platform | David Bello | Abuja | High | In Progress | 15000000 | 12000000 | 0 | 50 | 5 |  |  | 3000000
PRJ0026 | Access Bank | Mobile Banking App | John Iwoh | Abuja | High | Completed | 25000000 | 12000000 | 5 | 75 | 2 | 2024-10-22 | 2025-01-13 | 13000000
PRJ0027 | Zenith Bank | Erp Migration | David Bello | Abuja | Low | In Progress | 60000000 | 35000000 | 20 | 100 | 4 | 2024-12-16 | 2025-06-13 | 25000000
PRJ0028 | Access Bank | Ai Analytics Platform | Grace Adeyemi | Abuja | Medium | In Progress | 60000000 | 55000000 | 20 | 100 | 1 |  | 2024-04-03 | 5000000
PRJ0029 | Dangote Group | Cloud Infrastructure | Michael Dan | Kano | High | In Progress | 45000000 | 100000000 | 15 | 100 | 2 | 2024-05-21 |  | -55000000
PRJ0030 | Airtel | Crm Implementation | Sarah Musa | Lagos | High | In Progress | 25000000 | 12000000 | 5 | 50 | 1 |  | 2024-04-02 | 13000000
PRJ0031 | Gtbank | Cloud Infrastructure | David Bello | Port Harcourt | High | Delayed | 60000000 | 35000000 | 0 | 90 | 3 | 2025-01-22 | 2025-05-11 | 25000000
PRJ0032 | Uba | Mobile Banking App | Michael Dan | Kano | Low | Completed | 25000000 | 55000000 | 0 | 75 | 1 |  |  | -30000000
PRJ0033 | Nestle Nigeria | Mobile Banking App | Grace Adeyemi | Lagos | High | In Progress | 60000000 | 55000000 | 20 | 50 | 4 | 2024-04-20 |  | 5000000
PRJ0034 | Dangote Group | Cybersecurity Upgrade | Michael Dan | Abuja | Medium | Delayed | 120000000 | 55000000 | 20 | 50 | 1 |  | 2024-08-02 | 65000000
PRJ0035 | Nestle Nigeria | Cybersecurity Upgrade | David Bello | Abuja | Medium | In Progress | 45000000 | 100000000 | 10 | 0 | 2 |  |  | -55000000
PRJ0036 | Interswitch | Data Warehouse | Michael Dan | Lagos | Medium | Completed | 25000000 | 35000000 | 15 | 0 | 2 |  | 2024-11-12 | -10000000
PRJ0037 | Interswitch | Ai Analytics Platform | Michael Dan | Abuja | Medium | Delayed | 45000000 | 12000000 | 15 | 100 | 2 | 2024-05-27 | 2024-10-12 | 33000000
PRJ0038 | Zenith Bank | Mobile Banking App | David Bello | Kano | High | In Progress | 15000000 | 20000000 | 15 | 75 | 3 |  |  | -5000000
PRJ0039 | Gtbank | Mobile Banking App | Sarah Musa | Lagos | High | Delayed | 25000000 | 55000000 | 10 | 0 | 3 |  |  | -30000000
PRJ0040 | Interswitch | Mobile Banking App | Grace Adeyemi | Abuja | Medium | Completed | 120000000 | 100000000 | 10 | 100 | 4 | 2025-01-21 |  | 20000000
PRJ0041 | Access Bank | Data Warehouse | David Bello | Port Harcourt | High | In Progress | 120000000 | 55000000 | 15 | 0 | 4 |  | 2025-01-25 | 65000000
PRJ0042 | Flutterwave | Erp Migration | Sarah Musa | Kano | Medium | Completed | 15000000 | 35000000 | 20 | 0 | 3 |  |  | -20000000
PRJ0043 | Dangote Group | Erp Migration | Sarah Musa | Abuja | Medium | In Progress | 15000000 | 55000000 | 0 | 90 | 1 | 2025-01-20 |  | -40000000
PRJ0044 | Airtel | Erp Migration | Michael Dan | Abuja | Medium | Completed | 15000000 | 55000000 | 10 | 90 | 3 |  |  | -40000000
PRJ0045 | Airtel | Crm Implementation | Michael Dan | Abuja | Medium | In Progress | 120000000 | 12000000 | 15 | 100 | 4 |  |  | 108000000
PRJ0046 | Nestle Nigeria | Crm Implementation | Grace Adeyemi | Abuja | Low | Completed | 15000000 | 20000000 | 5 | 25 | 4 | 2024-02-23 |  | -5000000
PRJ0047 | Access Bank | Data Warehouse | Grace Adeyemi | Abuja | Medium | Delayed | 60000000 | 100000000 | 20 | 25 | 1 |  | 2025-04-29 | -40000000
PRJ0048 | Nestle Nigeria | Crm Implementation | David Bello | Port Harcourt | High | Delayed | 120000000 | 20000000 | 20 | 75 | 3 |  | 2024-08-29 | 100000000
PRJ0049 | Mtn Nigeria | Network Optimization | Sarah Musa | Kano | Medium | Delayed | 60000000 | 100000000 | 20 | 25 | 5 |  |  | -40000000
PRJ0050 | Mtn Nigeria | Cloud Infrastructure | Grace Adeyemi | Lagos | Medium | Delayed | 25000000 | 20000000 | 20 | 75 | 5 | 2024-06-12 |  | 5000000
PRJ0051 | Gtbank | Mobile Banking App | David Bello | Lagos | High | Completed | 15000000 | 55000000 | 15 | 75 | 3 |  |  | -40000000
PRJ0052 | Interswitch | Mobile Banking App | Grace Adeyemi | Lagos | Low | Delayed | 45000000 | 100000000 | 0 | 100 | 5 | 2024-12-20 | 2025-03-15 | -55000000
PRJ0053 | Uba | Cloud Infrastructure | Sarah Musa | Abuja | Medium | In Progress | 15000000 | 55000000 | 20 | 25 | 1 |  |  | -40000000
PRJ0054 | Interswitch | Cybersecurity Upgrade | Sarah Musa | Kano | Medium | Completed | 60000000 | 55000000 | 10 | 75 | 1 | 2024-11-24 |  | 5000000
PRJ0055 | Flutterwave | Cybersecurity Upgrade | David Bello | Abuja | Medium | Delayed | 60000000 | 12000000 | 10 | 0 | 2 | 2024-11-29 |  | 48000000
PRJ0056 | Flutterwave | Network Optimization | Sarah Musa | Kano | Medium | In Progress | 15000000 | 12000000 | 5 | 75 | 3 |  |  | 3000000
PRJ0057 | Airtel | Cloud Infrastructure | Grace Adeyemi | Port Harcourt | Low | In Progress | 25000000 | 100000000 | 15 | 100 | 2 |  | 2024-08-23 | -75000000
PRJ0058 | Gtbank | Erp Migration | David Bello | Abuja | Medium | Completed | 45000000 | 20000000 | 0 | 90 | 4 |  |  | 25000000
PRJ0059 | Interswitch | Ai Analytics Platform | David Bello | Lagos | High | Completed | 15000000 | 35000000 | 20 | 75 | 2 | 2024-01-31 |  | -20000000
PRJ0060 | Uba | Mobile Banking App | Sarah Musa | Lagos | High | In Progress | 60000000 | 12000000 | 5 | 25 | 3 |  |  | 48000000
PRJ0061 | Uba | Erp Migration | Sarah Musa | Abuja | High | Delayed | 45000000 | 55000000 | 10 | 90 | 4 |  |  | -10000000
PRJ0062 | Airtel | Mobile Banking App | John Iwoh | Port Harcourt | Medium | Delayed | 25000000 | 20000000 | 5 | 50 | 4 |  |  | 5000000
PRJ0063 | Nestle Nigeria | Network Optimization | Grace Adeyemi | Port Harcourt | Medium | In Progress | 120000000 | 35000000 | 15 | 100 | 4 |  | 2024-03-31 | 85000000
PRJ0064 | Mtn Nigeria | Network Optimization | Grace Adeyemi | Abuja | High | Completed | 25000000 | 20000000 | 5 | 25 | 5 |  | 2024-09-19 | 5000000
PRJ0065 | Flutterwave | Crm Implementation | Michael Dan | Abuja | Low | Delayed | 25000000 | 20000000 | 15 | 25 | 2 |  | 2024-09-26 | 5000000
PRJ0066 | Dangote Group | Mobile Banking App | David Bello | Lagos | Low | In Progress | 60000000 | 35000000 | 5 | 0 | 5 |  |  | 25000000
PRJ0067 | Dangote Group | Mobile Banking App | Grace Adeyemi | Port Harcourt | Low | In Progress | 60000000 | 20000000 | 15 | 25 | 2 |  |  | 40000000
PRJ0068 | Uba | Data Warehouse | David Bello | Kano | Medium | Completed | 120000000 | 12000000 | 15 | 90 | 2 | 2025-02-04 | 2025-06-01 | 108000000
PRJ0069 | Airtel | Network Optimization | John Iwoh | Lagos | Medium | Completed | 60000000 | 55000000 | 10 | 90 | 4 |  |  | 5000000
PRJ0070 | Interswitch | Data Warehouse | David Bello | Port Harcourt | Low | In Progress | 120000000 | 35000000 | 5 | 50 | 4 |  |  | 85000000
PRJ0071 | Dangote Group | Crm Implementation | Michael Dan | Lagos | High | Delayed | 45000000 | 35000000 | 20 | 0 | 3 | 2024-05-27 |  | 10000000
PRJ0072 | Nestle Nigeria | Data Warehouse | Sarah Musa | Lagos | High | Delayed | 45000000 | 55000000 | 15 | 25 | 3 |  | 2025-03-05 | -10000000
PRJ0073 | Dangote Group | Cybersecurity Upgrade | Sarah Musa | Abuja | High | Completed | 25000000 | 35000000 | 5 | 25 | 1 | 2024-06-18 | 2024-10-31 | -10000000
PRJ0074 | Gtbank | Erp Migration | David Bello | Abuja | High | Delayed | 25000000 | 100000000 | 0 | 0 | 2 |  | 2025-03-16 | -75000000
PRJ0075 | Dangote Group | Cybersecurity Upgrade | John Iwoh | Abuja | High | Completed | 15000000 | 100000000 | 20 | 50 | 2 |  |  | -85000000
PRJ0076 | Mtn Nigeria | Erp Migration | Sarah Musa | Kano | Low | In Progress | 45000000 | 35000000 | 0 | 75 | 4 |  |  | 10000000
PRJ0077 | Zenith Bank | Cybersecurity Upgrade | David Bello | Lagos | Medium | Completed | 15000000 | 100000000 | 5 | 75 | 2 |  | 2025-02-12 | -85000000
PRJ0078 | Uba | Network Optimization | David Bello | Port Harcourt | Medium | Completed | 60000000 | 100000000 | 5 | 0 | 3 |  |  | -40000000
PRJ0079 | Mtn Nigeria | Crm Implementation | Grace Adeyemi | Abuja | High | Delayed | 45000000 | 20000000 | 20 | 0 | 2 | 2024-02-21 |  | 25000000
PRJ0080 | Gtbank | Cloud Infrastructure | Michael Dan | Abuja | High | Completed | 45000000 | 20000000 | 20 | 100 | 4 | 2025-01-13 | 2025-04-01 | 25000000
PRJ0081 | Gtbank | Data Warehouse | John Iwoh | Abuja | Medium | Delayed | 60000000 | 35000000 | 20 | 50 | 1 |  |  | 25000000
PRJ0082 | Interswitch | Data Warehouse | David Bello | Kano | Medium | In Progress | 25000000 | 100000000 | 15 | 25 | 1 |  |  | -75000000
PRJ0083 | Uba | Mobile Banking App | John Iwoh | Lagos | Low | Delayed | 25000000 | 12000000 | 20 | 50 | 2 | 2024-09-06 |  | 13000000
PRJ0084 | Access Bank | Data Warehouse | David Bello | Kano | High | In Progress | 60000000 | 100000000 | 15 | 25 | 4 | 2024-09-27 | 2025-03-09 | -40000000
PRJ0085 | Dangote Group | Ai Analytics Platform | Sarah Musa | Port Harcourt | Medium | Delayed | 45000000 | 55000000 | 15 | 100 | 1 |  |  | -10000000
PRJ0086 | Flutterwave | Crm Implementation | David Bello | Kano | Medium | Delayed | 15000000 | 100000000 | 20 | 90 | 3 |  | 2024-01-31 | -85000000
PRJ0087 | Gtbank | Data Warehouse | Michael Dan | Port Harcourt | High | Completed | 25000000 | 35000000 | 10 | 90 | 5 |  |  | -10000000
PRJ0088 | Flutterwave | Cloud Infrastructure | Sarah Musa | Port Harcourt | High | Completed | 15000000 | 35000000 | 10 | 50 | 3 | 2024-01-27 | 2024-05-19 | -20000000
PRJ0089 | Zenith Bank | Cybersecurity Upgrade | Grace Adeyemi | Lagos | Medium | Completed | 60000000 | 100000000 | 10 | 25 | 4 | 2024-10-08 |  | -40000000
PRJ0090 | Nestle Nigeria | Mobile Banking App | Michael Dan | Lagos | Medium | Completed | 25000000 | 20000000 | 5 | 25 | 3 | 2024-04-11 | 2024-06-20 | 5000000
PRJ0091 | Zenith Bank | Ai Analytics Platform | Sarah Musa | Lagos | Medium | Delayed | 15000000 | 35000000 | 15 | 90 | 1 | 2024-10-25 |  | -20000000
PRJ0092 | Nestle Nigeria | Mobile Banking App | Sarah Musa | Port Harcourt | Medium | Completed | 15000000 | 20000000 | 5 | 50 | 2 |  |  | -5000000
PRJ0093 | Flutterwave | Cloud Infrastructure | Sarah Musa | Port Harcourt | Low | In Progress | 25000000 | 100000000 | 10 | 75 | 4 |  |  | -75000000
PRJ0094 | Nestle Nigeria | Cloud Infrastructure | Michael Dan | Abuja | Medium | In Progress | 60000000 | 100000000 | 0 | 75 | 1 |  |  | -40000000
PRJ0095 | Flutterwave | Network Optimization | Sarah Musa | Lagos | High | Delayed | 15000000 | 55000000 | 5 | 50 | 1 |  | 2024-10-30 | -40000000
PRJ0096 | Airtel | Erp Migration | David Bello | Lagos | Low | Delayed | 45000000 | 55000000 | 10 | 75 | 1 |  |  | -10000000
PRJ0097 | Zenith Bank | Crm Implementation | Grace Adeyemi | Abuja | High | Completed | 120000000 | 100000000 | 5 | 90 | 2 | 2024-06-15 | 2024-08-02 | 20000000
PRJ0098 | Uba | Cybersecurity Upgrade | Sarah Musa | Port Harcourt | Medium | Completed | 120000000 | 55000000 | 5 | 25 | 1 |  | 2024-11-14 | 65000000
PRJ0099 | Mtn Nigeria | Cybersecurity Upgrade | Michael Dan | Abuja | High | Completed | 120000000 | 100000000 | 10 | 0 | 4 |  | 2025-03-12 | 20000000
PRJ0100 | Nestle Nigeria | Erp Migration | John Iwoh | Port Harcourt | High | Completed | 120000000 | 100000000 | 15 | 90 | 5 |  |  | 20000000
PRJ0101 | Zenith Bank | Cloud Infrastructure | Sarah Musa | Abuja | Medium | Completed | 60000000 | 20000000 | 20 | 25 | 2 |  |  | 40000000
PRJ0102 | Mtn Nigeria | Erp Migration | David Bello | Kano | High | Completed | 45000000 | 20000000 | 5 | 25 | 5 |  |  | 25000000
PRJ0103 | Flutterwave | Mobile Banking App | David Bello | Lagos | Medium | Completed | 120000000 | 35000000 | 0 | 90 | 3 |  |  | 85000000
PRJ0104 | Interswitch | Network Optimization | John Iwoh | Lagos | Medium | In Progress | 25000000 | 12000000 | 20 | 90 | 1 | 2024-12-30 |  | 13000000
PRJ0105 | Zenith Bank | Network Optimization | Sarah Musa | Abuja | High | Delayed | 25000000 | 55000000 | 15 | 75 | 3 |  |  | -30000000
PRJ0106 | Interswitch | Cloud Infrastructure | Grace Adeyemi | Abuja | Medium | Completed | 120000000 | 20000000 | 0 | 90 | 4 | 2024-10-31 |  | 100000000
PRJ0107 | Gtbank | Cloud Infrastructure | David Bello | Abuja | Medium | Completed | 45000000 | 20000000 | 5 | 0 | 2 |  |  | 25000000
PRJ0108 | Access Bank | Mobile Banking App | Michael Dan | Lagos | Low | Completed | 45000000 | 35000000 | 10 | 25 | 3 | 2024-02-23 |  | 10000000
PRJ0109 | Nestle Nigeria | Data Warehouse | John Iwoh | Abuja | Medium | Completed | 60000000 | 55000000 | 15 | 75 | 5 | 2024-10-14 |  | 5000000
PRJ0110 | Dangote Group | Erp Migration | Grace Adeyemi | Abuja | High | In Progress | 60000000 | 12000000 | 20 | 25 | 2 | 2024-12-28 | 2025-05-12 | 48000000
PRJ0111 | Mtn Nigeria | Crm Implementation | Sarah Musa | Lagos | Medium | Completed | 45000000 | 20000000 | 5 | 0 | 3 | 2024-05-09 |  | 25000000
PRJ0112 | Gtbank | Crm Implementation | Sarah Musa | Kano | Medium | Completed | 25000000 | 12000000 | 0 | 50 | 3 |  | 2025-04-03 | 13000000
PRJ0113 | Interswitch | Cybersecurity Upgrade | Grace Adeyemi | Lagos | High | Delayed | 15000000 | 100000000 | 15 | 0 | 5 |  | 2024-09-20 | -85000000
PRJ0114 | Mtn Nigeria | Cloud Infrastructure | Michael Dan | Kano | Low | Delayed | 25000000 | 55000000 | 20 | 50 | 4 |  | 2025-04-18 | -30000000
PRJ0115 | Nestle Nigeria | Ai Analytics Platform | David Bello | Kano | Low | Delayed | 25000000 | 35000000 | 15 | 75 | 5 | 2024-03-13 | 2024-06-17 | -10000000
PRJ0116 | Nestle Nigeria | Ai Analytics Platform | John Iwoh | Abuja | Medium | Delayed | 60000000 | 35000000 | 20 | 50 | 4 | 2024-11-17 |  | 25000000
PRJ0117 | Airtel | Crm Implementation | David Bello | Abuja | Medium | Completed | 45000000 | 100000000 | 20 | 25 | 2 |  |  | -55000000
PRJ0118 | Zenith Bank | Network Optimization | David Bello | Abuja | Medium | Delayed | 45000000 | 12000000 | 20 | 25 | 3 |  |  | 33000000
PRJ0119 | Interswitch | Data Warehouse | Grace Adeyemi | Lagos | Low | In Progress | 120000000 | 100000000 | 15 | 75 | 5 | 2024-12-15 |  | 20000000
PRJ0120 | Gtbank | Network Optimization | Michael Dan | Lagos | High | Delayed | 120000000 | 100000000 | 10 | 50 | 3 |  | 2025-02-03 | 20000000
PRJ0121 | Mtn Nigeria | Data Warehouse | David Bello | Abuja | Medium | Delayed | 60000000 | 55000000 | 5 | 90 | 1 | 2024-03-11 |  | 5000000
PRJ0122 | Interswitch | Ai Analytics Platform | Michael Dan | Kano | Medium | Delayed | 60000000 | 12000000 | 5 | 25 | 1 | 2024-06-30 |  | 48000000
PRJ0123 | Zenith Bank | Data Warehouse | Michael Dan | Abuja | Medium | Delayed | 15000000 | 12000000 | 0 | 75 | 1 | 2024-09-09 | 2024-12-14 | 3000000
PRJ0124 | Mtn Nigeria | Data Warehouse | David Bello | Lagos | High | In Progress | 60000000 | 35000000 | 5 | 50 | 5 |  |  | 25000000
PRJ0125 | Zenith Bank | Crm Implementation | Sarah Musa | Abuja | High | Completed | 120000000 | 55000000 | 5 | 0 | 4 | 2025-01-08 |  | 65000000
PRJ0126 | Interswitch | Cybersecurity Upgrade | Sarah Musa | Abuja | High | Completed | 25000000 | 100000000 | 20 | 0 | 4 | 2024-07-04 |  | -75000000
PRJ0127 | Flutterwave | Network Optimization | Michael Dan | Abuja | High | In Progress | 25000000 | 12000000 | 20 | 100 | 3 | 2024-07-12 |  | 13000000
PRJ0128 | Uba | Cybersecurity Upgrade | Grace Adeyemi | Kano | High | Completed | 15000000 | 20000000 | 5 | 25 | 5 |  |  | -5000000
PRJ0129 | Access Bank | Crm Implementation | David Bello | Kano | High | In Progress | 45000000 | 55000000 | 20 | 100 | 3 | 2024-05-14 | 2024-07-28 | -10000000
PRJ0130 | Interswitch | Data Warehouse | Michael Dan | Lagos | High | In Progress | 60000000 | 20000000 | 5 | 75 | 5 | 2024-09-13 | 2024-11-18 | 40000000
PRJ0131 | Flutterwave | Data Warehouse | Grace Adeyemi | Abuja | Medium | Delayed | 45000000 | 55000000 | 0 | 100 | 4 |  |  | -10000000
PRJ0132 | Gtbank | Crm Implementation | Grace Adeyemi | Kano | Medium | In Progress | 60000000 | 12000000 | 5 | 0 | 3 |  |  | 48000000
PRJ0133 | Airtel | Cybersecurity Upgrade | David Bello | Lagos | High | Completed | 120000000 | 20000000 | 20 | 0 | 2 | 2025-01-13 |  | 100000000
PRJ0134 | Interswitch | Network Optimization | Grace Adeyemi | Port Harcourt | High | Delayed | 45000000 | 20000000 | 0 | 100 | 2 |  |  | 25000000
PRJ0135 | Zenith Bank | Cybersecurity Upgrade | David Bello | Abuja | Medium | Delayed | 15000000 | 35000000 | 20 | 25 | 5 |  | 2024-03-13 | -20000000
PRJ0136 | Airtel | Cybersecurity Upgrade | Michael Dan | Kano | Medium | In Progress | 120000000 | 35000000 | 5 | 0 | 3 | 2024-06-05 |  | 85000000
PRJ0137 | Gtbank | Cybersecurity Upgrade | John Iwoh | Abuja | Medium | Completed | 25000000 | 12000000 | 0 | 90 | 3 | 2024-06-26 | 2024-10-14 | 13000000
PRJ0138 | Nestle Nigeria | Data Warehouse | David Bello | Abuja | High | In Progress | 60000000 | 35000000 | 20 | 75 | 1 |  |  | 25000000
PRJ0139 | Access Bank | Network Optimization | Grace Adeyemi | Abuja | High | In Progress | 25000000 | 20000000 | 15 | 90 | 2 | 2025-01-05 |  | 5000000
PRJ0140 | Zenith Bank | Cybersecurity Upgrade | Sarah Musa | Abuja | Medium | Completed | 15000000 | 20000000 | 0 | 0 | 1 |  |  | -5000000
PRJ0141 | Uba | Network Optimization | Michael Dan | Lagos | Low | In Progress | 120000000 | 100000000 | 20 | 50 | 5 |  |  | 20000000
PRJ0142 | Gtbank | Data Warehouse | John Iwoh | Abuja | High | Delayed | 25000000 | 55000000 | 0 | 0 | 1 |  |  | -30000000
PRJ0143 | Interswitch | Data Warehouse | Grace Adeyemi | Port Harcourt | High | In Progress | 60000000 | 100000000 | 20 | 50 | 4 |  |  | -40000000
PRJ0144 | Airtel | Cybersecurity Upgrade | David Bello | Lagos | Medium | In Progress | 45000000 | 35000000 | 5 | 100 | 3 |  |  | 10000000
PRJ0145 | Access Bank | Network Optimization | David Bello | Abuja | High | In Progress | 60000000 | 100000000 | 5 | 100 | 1 |  | 2025-02-28 | -40000000
PRJ0146 | Zenith Bank | Data Warehouse | Grace Adeyemi | Abuja | High | Delayed | 120000000 | 100000000 | 15 | 50 | 1 | 2024-03-23 | 2024-08-25 | 20000000
PRJ0147 | Gtbank | Network Optimization | Michael Dan | Lagos | Medium | Delayed | 15000000 | 12000000 | 5 | 75 | 1 | 2024-10-15 |  | 3000000
PRJ0148 | Mtn Nigeria | Data Warehouse | Grace Adeyemi | Abuja | Medium | Delayed | 60000000 | 20000000 | 5 | 100 | 4 |  |  | 40000000
PRJ0149 | Access Bank | Erp Migration | David Bello | Abuja | Low | Delayed | 25000000 | 100000000 | 15 | 25 | 5 |  |  | -75000000
PRJ0150 | Airtel | Crm Implementation | David Bello | Lagos | High | In Progress | 25000000 | 100000000 | 0 | 0 | 5 |  | 2024-12-17 | -75000000
PRJ0151 | Gtbank | Erp Migration | Sarah Musa | Port Harcourt | High | Delayed | 25000000 | 20000000 | 0 | 0 | 4 |  | 2024-07-24 | 5000000
PRJ0152 | Dangote Group | Erp Migration | Sarah Musa | Lagos | Medium | In Progress | 60000000 | 100000000 | 15 | 50 | 3 |  |  | -40000000
PRJ0153 | Dangote Group | Cybersecurity Upgrade | David Bello | Abuja | Medium | Completed | 45000000 | 20000000 | 5 | 0 | 5 |  | 2025-06-06 | 25000000
PRJ0154 | Airtel | Cloud Infrastructure | David Bello | Abuja | High | In Progress | 45000000 | 35000000 | 10 | 90 | 3 | 2024-07-29 |  | 10000000
PRJ0155 | Dangote Group | Crm Implementation | Grace Adeyemi | Lagos | Medium | Completed | 60000000 | 12000000 | 5 | 25 | 3 |  | 2024-08-26 | 48000000
PRJ0156 | Zenith Bank | Data Warehouse | John Iwoh | Lagos | High | Completed | 25000000 | 12000000 | 20 | 50 | 2 |  | 2024-12-16 | 13000000
PRJ0157 | Uba | Cybersecurity Upgrade | Grace Adeyemi | Lagos | High | Completed | 60000000 | 100000000 | 20 | 50 | 3 |  |  | -40000000
PRJ0158 | Nestle Nigeria | Network Optimization | Sarah Musa | Kano | Medium | Delayed | 25000000 | 35000000 | 5 | 75 | 5 |  |  | -10000000
PRJ0159 | Dangote Group | Mobile Banking App | John Iwoh | Lagos | Low | Delayed | 25000000 | 12000000 | 20 | 75 | 5 | 2024-09-13 |  | 13000000
PRJ0160 | Nestle Nigeria | Network Optimization | Michael Dan | Lagos | High | Delayed | 45000000 | 20000000 | 0 | 25 | 1 | 2024-04-01 |  | 25000000
PRJ0161 | Mtn Nigeria | Ai Analytics Platform | Grace Adeyemi | Port Harcourt | Low | Delayed | 120000000 | 55000000 | 5 | 90 | 2 |  |  | 65000000
PRJ0162 | Dangote Group | Cloud Infrastructure | John Iwoh | Kano | Medium | Delayed | 15000000 | 20000000 | 0 | 0 | 1 |  | 2025-04-13 | -5000000
PRJ0163 | Flutterwave | Cloud Infrastructure | Michael Dan | Kano | Medium | Delayed | 45000000 | 20000000 | 5 | 90 | 1 | 2024-08-09 | 2025-01-22 | 25000000
PRJ0164 | Uba | Erp Migration | Grace Adeyemi | Lagos | Medium | Completed | 45000000 | 35000000 | 15 | 100 | 3 | 2024-03-10 | 2024-06-28 | 10000000
PRJ0165 | Gtbank | Data Warehouse | David Bello | Abuja | Medium | Delayed | 120000000 | 12000000 | 0 | 75 | 3 |  | 2024-05-05 | 108000000
PRJ0166 | Uba | Data Warehouse | Michael Dan | Abuja | Medium | Completed | 15000000 | 35000000 | 15 | 90 | 1 |  | 2024-10-04 | -20000000
PRJ0167 | Flutterwave | Crm Implementation | Grace Adeyemi | Port Harcourt | High | Completed | 15000000 | 20000000 | 5 | 75 | 1 | 2025-01-31 |  | -5000000
PRJ0168 | Dangote Group | Cybersecurity Upgrade | Michael Dan | Kano | Medium | Completed | 15000000 | 12000000 | 0 | 75 | 3 |  | 2024-05-04 | 3000000
PRJ0169 | Uba | Cybersecurity Upgrade | Sarah Musa | Port Harcourt | High | Completed | 45000000 | 12000000 | 15 | 100 | 4 | 2024-09-06 |  | 33000000
PRJ0170 | Dangote Group | Crm Implementation | Michael Dan | Lagos | Medium | Delayed | 60000000 | 100000000 | 10 | 75 | 5 |  | 2024-12-02 | -40000000
PRJ0171 | Gtbank | Data Warehouse | Sarah Musa | Lagos | Medium | In Progress | 120000000 | 12000000 | 15 | 75 | 2 | 2024-05-13 |  | 108000000
PRJ0172 | Access Bank | Erp Migration | Sarah Musa | Lagos | Medium | Delayed | 45000000 | 35000000 | 20 | 75 | 4 |  |  | 10000000
PRJ0173 | Flutterwave | Ai Analytics Platform | David Bello | Lagos | High | Completed | 25000000 | 100000000 | 5 | 25 | 3 | 2024-01-21 |  | -75000000
PRJ0174 | Zenith Bank | Network Optimization | David Bello | Lagos | Medium | In Progress | 60000000 | 100000000 | 10 | 75 | 2 |  | 2024-12-24 | -40000000
PRJ0175 | Dangote Group | Data Warehouse | Grace Adeyemi | Kano | High | In Progress | 120000000 | 55000000 | 0 | 90 | 2 |  |  | 65000000
PRJ0176 | Access Bank | Network Optimization | Sarah Musa | Abuja | Medium | Completed | 25000000 | 12000000 | 20 | 50 | 3 |  |  | 13000000
PRJ0177 | Nestle Nigeria | Ai Analytics Platform | John Iwoh | Abuja | High | Completed | 45000000 | 100000000 | 5 | 50 | 3 |  | 2024-06-08 | -55000000
PRJ0178 | Interswitch | Cloud Infrastructure | Sarah Musa | Kano | Low | Completed | 25000000 | 55000000 | 20 | 100 | 2 |  | 2025-03-06 | -30000000
PRJ0179 | Access Bank | Mobile Banking App | Sarah Musa | Lagos | Medium | Completed | 25000000 | 35000000 | 20 | 50 | 5 | 2024-07-02 | 2024-12-20 | -10000000
PRJ0180 | Airtel | Mobile Banking App | Michael Dan | Port Harcourt | High | In Progress | 25000000 | 55000000 | 0 | 90 | 5 | 2024-05-31 |  | -30000000
PRJ0181 | Zenith Bank | Network Optimization | Michael Dan | Abuja | Medium | Completed | 15000000 | 12000000 | 20 | 90 | 4 |  |  | 3000000
PRJ0182 | Flutterwave | Erp Migration | Sarah Musa | Kano | Medium | In Progress | 45000000 | 12000000 | 0 | 100 | 4 | 2025-01-10 |  | 33000000
PRJ0183 | Gtbank | Cybersecurity Upgrade | Sarah Musa | Abuja | Low | In Progress | 15000000 | 20000000 | 5 | 0 | 1 | 2024-08-16 |  | -5000000
PRJ0184 | Mtn Nigeria | Crm Implementation | John Iwoh | Kano | Medium | Completed | 120000000 | 12000000 | 5 | 100 | 4 | 2024-01-27 |  | 108000000
PRJ0185 | Uba | Mobile Banking App | Grace Adeyemi | Lagos | Low | Completed | 45000000 | 100000000 | 20 | 75 | 2 |  |  | -55000000
PRJ0186 | Zenith Bank | Cloud Infrastructure | Sarah Musa | Kano | Medium | Delayed | 45000000 | 12000000 | 15 | 0 | 3 |  |  | 33000000
PRJ0187 | Flutterwave | Data Warehouse | John Iwoh | Abuja | Medium | Completed | 60000000 | 55000000 | 5 | 75 | 1 |  |  | 5000000
PRJ0188 | Interswitch | Crm Implementation | Sarah Musa | Port Harcourt | Medium | In Progress | 60000000 | 12000000 | 10 | 100 | 1 | 2024-10-29 | 2025-02-11 | 48000000
PRJ0189 | Interswitch | Cybersecurity Upgrade | John Iwoh | Kano | Low | Delayed | 45000000 | 20000000 | 15 | 0 | 5 | 2024-10-20 |  | 25000000
PRJ0190 | Airtel | Erp Migration | John Iwoh | Port Harcourt | Medium | Delayed | 45000000 | 100000000 | 20 | 0 | 5 |  | 2025-05-20 | -55000000
PRJ0191 | Mtn Nigeria | Ai Analytics Platform | Grace Adeyemi | Port Harcourt | High | In Progress | 45000000 | 100000000 | 20 | 75 | 1 |  |  | -55000000
PRJ0192 | Flutterwave | Cloud Infrastructure | David Bello | Kano | High | Completed | 15000000 | 20000000 | 5 | 75 | 2 | 2024-05-24 | 2024-10-08 | -5000000
PRJ0193 | Access Bank | Erp Migration | Michael Dan | Lagos | High | In Progress | 60000000 | 55000000 | 5 | 50 | 1 | 2024-01-23 |  | 5000000
PRJ0194 | Dangote Group | Cybersecurity Upgrade | Michael Dan | Abuja | Low | In Progress | 60000000 | 20000000 | 15 | 25 | 4 | 2024-06-03 | 2024-11-16 | 40000000
PRJ0195 | Gtbank | Mobile Banking App | John Iwoh | Lagos | Medium | Completed | 25000000 | 55000000 | 15 | 0 | 1 |  | 2024-12-31 | -30000000
PRJ0196 | Flutterwave | Crm Implementation | Sarah Musa | Port Harcourt | High | In Progress | 25000000 | 100000000 | 0 | 90 | 1 | 2024-10-12 | 2024-11-11 | -75000000
PRJ0197 | Zenith Bank | Ai Analytics Platform | Sarah Musa | Lagos | Medium | In Progress | 120000000 | 12000000 | 5 | 25 | 3 | 2024-01-31 |  | 108000000
PRJ0198 | Flutterwave | Crm Implementation | Sarah Musa | Kano | Medium | Delayed | 15000000 | 12000000 | 5 | 90 | 4 |  | 2024-11-30 | 3000000
PRJ0199 | Zenith Bank | Cloud Infrastructure | Grace Adeyemi | Abuja | Medium | Delayed | 120000000 | 35000000 | 10 | 0 | 5 | 2024-01-25 | 2024-06-11 | 85000000
PRJ0200 | Mtn Nigeria | Cybersecurity Upgrade | John Iwoh | Kano | High | In Progress | 25000000 | 12000000 | 20 | 25 | 3 |  |  | 13000000
PRJ0201 | Interswitch | Cybersecurity Upgrade | Michael Dan | Abuja | High | Delayed | 25000000 | 100000000 | 10 | 50 | 5 |  |  | -75000000
PRJ0202 | Airtel | Crm Implementation | David Bello | Abuja | High | Delayed | 120000000 | 12000000 | 0 | 90 | 4 |  |  | 108000000
PRJ0203 | Nestle Nigeria | Erp Migration | Sarah Musa | Lagos | High | Delayed | 45000000 | 100000000 | 15 | 25 | 1 |  |  | -55000000
PRJ0204 | Flutterwave | Mobile Banking App | John Iwoh | Kano | High | Completed | 60000000 | 100000000 | 0 | 25 | 4 |  |  | -40000000
PRJ0205 | Nestle Nigeria | Data Warehouse | David Bello | Lagos | Low | Completed | 15000000 | 20000000 | 20 | 75 | 4 |  |  | -5000000
PRJ0206 | Nestle Nigeria | Cloud Infrastructure | Grace Adeyemi | Abuja | High | In Progress | 120000000 | 35000000 | 20 | 75 | 1 | 2024-11-04 | 2025-03-19 | 85000000
PRJ0207 | Gtbank | Ai Analytics Platform | Grace Adeyemi | Lagos | Medium | Completed | 60000000 | 12000000 | 0 | 50 | 2 |  |  | 48000000
PRJ0208 | Gtbank | Data Warehouse | Michael Dan | Abuja | Low | Completed | 25000000 | 55000000 | 5 | 0 | 3 |  |  | -30000000
PRJ0209 | Zenith Bank | Network Optimization | John Iwoh | Port Harcourt | High | In Progress | 45000000 | 12000000 | 0 | 25 | 3 | 2024-03-25 |  | 33000000
PRJ0210 | Zenith Bank | Ai Analytics Platform | Grace Adeyemi | Abuja | Low | In Progress | 120000000 | 100000000 | 5 | 50 | 1 |  |  | 20000000
PRJ0211 | Dangote Group | Mobile Banking App | John Iwoh | Abuja | Medium | In Progress | 45000000 | 35000000 | 10 | 90 | 3 |  |  | 10000000
PRJ0212 | Access Bank | Network Optimization | Michael Dan | Lagos | Medium | Delayed | 15000000 | 20000000 | 15 | 25 | 2 |  |  | -5000000
PRJ0213 | Access Bank | Cybersecurity Upgrade | Michael Dan | Lagos | High | Completed | 45000000 | 20000000 | 10 | 100 | 4 |  |  | 25000000
PRJ0214 | Interswitch | Erp Migration | Michael Dan | Lagos | High | Completed | 15000000 | 100000000 | 5 | 75 | 2 | 2024-06-30 |  | -85000000
PRJ0215 | Airtel | Network Optimization | Sarah Musa | Abuja | Medium | Delayed | 45000000 | 100000000 | 10 | 25 | 4 |  | 2024-06-19 | -55000000
PRJ0216 | Flutterwave | Cloud Infrastructure | Grace Adeyemi | Lagos | Medium | Completed | 120000000 | 12000000 | 0 | 0 | 3 | 2024-06-24 |  | 108000000
PRJ0217 | Access Bank | Cloud Infrastructure | Sarah Musa | Lagos | High | In Progress | 25000000 | 35000000 | 0 | 0 | 3 |  | 2024-07-31 | -10000000
PRJ0218 | Access Bank | Cloud Infrastructure | Michael Dan | Lagos | Low | Completed | 60000000 | 20000000 | 0 | 100 | 1 |  |  | 40000000
PRJ0219 | Access Bank | Cloud Infrastructure | David Bello | Lagos | Medium | Completed | 120000000 | 100000000 | 10 | 25 | 1 | 2024-06-18 |  | 20000000
PRJ0220 | Dangote Group | Crm Implementation | Michael Dan | Lagos | High | Delayed | 120000000 | 12000000 | 20 | 100 | 5 |  |  | 108000000
PRJ0221 | Nestle Nigeria | Ai Analytics Platform | Sarah Musa | Abuja | Low | Delayed | 60000000 | 100000000 | 20 | 50 | 4 |  | 2024-12-17 | -40000000
PRJ0222 | Interswitch | Cybersecurity Upgrade | Grace Adeyemi | Abuja | Low | Delayed | 60000000 | 55000000 | 5 | 100 | 5 |  |  | 5000000
PRJ0223 | Nestle Nigeria | Erp Migration | Grace Adeyemi | Lagos | Medium | Delayed | 25000000 | 55000000 | 15 | 75 | 1 | 2025-01-01 |  | -30000000
PRJ0224 | Gtbank | Crm Implementation | Michael Dan | Lagos | High | Delayed | 15000000 | 35000000 | 5 | 50 | 3 | 2024-07-08 | 2024-08-04 | -20000000
PRJ0225 | Mtn Nigeria | Crm Implementation | Michael Dan | Port Harcourt | Medium | Delayed | 15000000 | 55000000 | 5 | 25 | 2 | 2024-08-13 | 2024-12-03 | -40000000
PRJ0226 | Interswitch | Erp Migration | Sarah Musa | Lagos | Medium | Completed | 45000000 | 100000000 | 0 | 25 | 3 |  |  | -55000000
PRJ0227 | Flutterwave | Data Warehouse | Michael Dan | Kano | Medium | In Progress | 45000000 | 55000000 | 15 | 25 | 5 |  |  | -10000000
PRJ0228 | Zenith Bank | Cloud Infrastructure | Michael Dan | Kano | High | Completed | 60000000 | 12000000 | 0 | 75 | 4 |  |  | 48000000
PRJ0229 | Nestle Nigeria | Ai Analytics Platform | Grace Adeyemi | Abuja | Medium | Completed | 45000000 | 100000000 | 10 | 50 | 2 |  | 2025-04-20 | -55000000
PRJ0230 | Interswitch | Ai Analytics Platform | Michael Dan | Abuja | Low | In Progress | 45000000 | 55000000 | 20 | 50 | 1 |  |  | -10000000
PRJ0231 | Mtn Nigeria | Mobile Banking App | Michael Dan | Abuja | High | Delayed | 60000000 | 100000000 | 10 | 25 | 5 |  | 2024-06-24 | -40000000
PRJ0232 | Dangote Group | Mobile Banking App | John Iwoh | Port Harcourt | High | In Progress | 45000000 | 12000000 | 0 | 0 | 3 |  |  | 33000000
PRJ0233 | Zenith Bank | Crm Implementation | David Bello | Kano | Medium | Completed | 60000000 | 12000000 | 10 | 75 | 1 |  |  | 48000000
PRJ0234 | Flutterwave | Crm Implementation | Grace Adeyemi | Port Harcourt | High | In Progress | 60000000 | 35000000 | 20 | 0 | 1 | 2024-12-09 |  | 25000000
PRJ0235 | Dangote Group | Crm Implementation | Sarah Musa | Abuja | High | In Progress | 45000000 | 20000000 | 15 | 90 | 1 |  |  | 25000000
PRJ0236 | Uba | Erp Migration | John Iwoh | Lagos | Medium | Completed | 120000000 | 20000000 | 5 | 25 | 4 | 2024-10-01 |  | 100000000
PRJ0237 | Interswitch | Crm Implementation | John Iwoh | Lagos | High | In Progress | 15000000 | 20000000 | 10 | 0 | 2 |  |  | -5000000
PRJ0238 | Access Bank | Crm Implementation | David Bello | Abuja | Low | Completed | 15000000 | 12000000 | 0 | 50 | 5 | 2024-01-25 |  | 3000000
PRJ0239 | Flutterwave | Data Warehouse | Sarah Musa | Kano | Low | Completed | 25000000 | 100000000 | 15 | 90 | 1 |  |  | -75000000
PRJ0240 | Nestle Nigeria | Cloud Infrastructure | David Bello | Port Harcourt | High | Completed | 60000000 | 55000000 | 5 | 0 | 5 | 2024-06-20 |  | 5000000
PRJ0241 | Nestle Nigeria | Erp Migration | David Bello | Abuja | Medium | Delayed | 45000000 | 100000000 | 20 | 0 | 1 |  |  | -55000000
PRJ0242 | Interswitch | Ai Analytics Platform | Michael Dan | Kano | Medium | Completed | 15000000 | 20000000 | 15 | 0 | 1 |  |  | -5000000
PRJ0243 | Flutterwave | Erp Migration | Sarah Musa | Lagos | Low | Completed | 60000000 | 55000000 | 20 | 25 | 1 | 2024-11-19 | 2025-01-28 | 5000000
PRJ0244 | Nestle Nigeria | Mobile Banking App | David Bello | Lagos | High | Delayed | 60000000 | 20000000 | 20 | 75 | 2 | 2024-12-18 |  | 40000000
PRJ0245 | Access Bank | Crm Implementation | David Bello | Port Harcourt | Low | Delayed | 120000000 | 12000000 | 10 | 0 | 2 |  | 2024-08-16 | 108000000
PRJ0246 | Access Bank | Crm Implementation | Sarah Musa | Port Harcourt | High | In Progress | 45000000 | 12000000 | 10 | 0 | 2 |  |  | 33000000
PRJ0247 | Dangote Group | Cloud Infrastructure | Grace Adeyemi | Port Harcourt | Low | Delayed | 15000000 | 12000000 | 15 | 50 | 2 |  |  | 3000000
PRJ0248 | Zenith Bank | Data Warehouse | David Bello | Port Harcourt | High | In Progress | 60000000 | 12000000 | 10 | 50 | 2 |  |  | 48000000
PRJ0249 | Airtel | Mobile Banking App | Sarah Musa | Port Harcourt | High | In Progress | 15000000 | 12000000 | 20 | 75 | 3 |  | 2024-05-03 | 3000000
PRJ0250 | Dangote Group | Crm Implementation | Sarah Musa | Port Harcourt | Low | Delayed | 45000000 | 100000000 | 0 | 100 | 1 | 2024-11-25 |  | -55000000
PRJ0251 | Gtbank | Cloud Infrastructure | Grace Adeyemi | Port Harcourt | Medium | In Progress | 25000000 | 20000000 | 20 | 100 | 3 |  |  | 5000000
PRJ0252 | Mtn Nigeria | Cybersecurity Upgrade | Sarah Musa | Lagos | High | In Progress | 120000000 | 35000000 | 20 | 90 | 5 | 2024-02-10 |  | 85000000
PRJ0253 | Uba | Ai Analytics Platform | David Bello | Port Harcourt | Low | Delayed | 15000000 | 12000000 | 0 | 0 | 4 |  | 2024-10-21 | 3000000
PRJ0254 | Interswitch | Ai Analytics Platform | Michael Dan | Lagos | Medium | Delayed | 15000000 | 55000000 | 0 | 90 | 1 | 2024-03-18 | 2024-09-07 | -40000000
PRJ0255 | Gtbank | Mobile Banking App | Grace Adeyemi | Port Harcourt | Medium | Delayed | 120000000 | 35000000 | 5 | 0 | 2 |  |  | 85000000
PRJ0256 | Access Bank | Cloud Infrastructure | John Iwoh | Abuja | Medium | Completed | 25000000 | 35000000 | 0 | 90 | 4 | 2025-01-09 |  | -10000000
PRJ0257 | Airtel | Mobile Banking App | Michael Dan | Abuja | Low | Delayed | 25000000 | 20000000 | 5 | 100 | 3 |  |  | 5000000
PRJ0258 | Airtel | Cloud Infrastructure | David Bello | Abuja | High | In Progress | 25000000 | 20000000 | 10 | 75 | 4 |  |  | 5000000
PRJ0259 | Nestle Nigeria | Mobile Banking App | John Iwoh | Port Harcourt | Medium | Completed | 60000000 | 100000000 | 10 | 0 | 3 |  | 2025-05-23 | -40000000
PRJ0260 | Airtel | Crm Implementation | John Iwoh | Lagos | Medium | Delayed | 60000000 | 35000000 | 5 | 25 | 5 |  | 2025-06-25 | 25000000
PRJ0261 | Interswitch | Cloud Infrastructure | Michael Dan | Lagos | High | Completed | 25000000 | 20000000 | 5 | 50 | 2 | 2024-07-11 |  | 5000000
PRJ0262 | Flutterwave | Data Warehouse | Grace Adeyemi | Lagos | High | In Progress | 25000000 | 55000000 | 15 | 75 | 5 | 2024-11-17 |  | -30000000
PRJ0263 | Gtbank | Network Optimization | John Iwoh | Kano | High | Completed | 15000000 | 35000000 | 20 | 90 | 5 |  |  | -20000000
PRJ0264 | Interswitch | Ai Analytics Platform | Sarah Musa | Lagos | Medium | In Progress | 15000000 | 20000000 | 0 | 90 | 2 | 2024-04-21 |  | -5000000
PRJ0265 | Uba | Mobile Banking App | Sarah Musa | Kano | Medium | In Progress | 15000000 | 100000000 | 0 | 100 | 2 |  |  | -85000000
PRJ0266 | Dangote Group | Ai Analytics Platform | Grace Adeyemi | Abuja | High | Delayed | 60000000 | 100000000 | 20 | 0 | 3 | 2024-09-21 |  | -40000000
PRJ0267 | Zenith Bank | Erp Migration | David Bello | Lagos | High | Delayed | 120000000 | 100000000 | 10 | 0 | 4 | 2024-02-02 |  | 20000000
PRJ0268 | Airtel | Ai Analytics Platform | Sarah Musa | Lagos | High | Delayed | 45000000 | 100000000 | 10 | 75 | 3 |  | 2024-07-14 | -55000000
PRJ0269 | Airtel | Cloud Infrastructure | Michael Dan | Abuja | Medium | Completed | 45000000 | 35000000 | 5 | 90 | 1 | 2024-11-01 |  | 10000000
PRJ0270 | Gtbank | Cloud Infrastructure | Sarah Musa | Port Harcourt | Low | Delayed | 45000000 | 12000000 | 5 | 100 | 1 |  | 2025-06-02 | 33000000
PRJ0271 | Flutterwave | Ai Analytics Platform | Grace Adeyemi | Port Harcourt | Medium | In Progress | 45000000 | 35000000 | 10 | 50 | 4 |  | 2024-03-18 | 10000000
PRJ0272 | Dangote Group | Mobile Banking App | David Bello | Kano | Medium | Delayed | 15000000 | 12000000 | 0 | 50 | 2 |  | 2024-06-17 | 3000000
PRJ0273 | Nestle Nigeria | Cybersecurity Upgrade | Sarah Musa | Abuja | Low | Delayed | 120000000 | 55000000 | 10 | 100 | 1 |  |  | 65000000
PRJ0274 | Interswitch | Data Warehouse | David Bello | Abuja | Medium | Completed | 15000000 | 55000000 | 10 | 50 | 1 |  |  | -40000000
PRJ0275 | Mtn Nigeria | Ai Analytics Platform | Grace Adeyemi | Port Harcourt | Low | Completed | 60000000 | 100000000 | 10 | 100 | 1 |  |  | -40000000
PRJ0276 | Dangote Group | Crm Implementation | David Bello | Lagos | Low | In Progress | 25000000 | 55000000 | 5 | 50 | 5 |  |  | -30000000
PRJ0277 | Dangote Group | Cloud Infrastructure | David Bello | Abuja | Low | Delayed | 120000000 | 100000000 | 0 | 100 | 1 |  |  | 20000000
PRJ0278 | Interswitch | Erp Migration | David Bello | Abuja | High | Delayed | 25000000 | 55000000 | 0 | 75 | 2 |  | 2024-09-18 | -30000000
PRJ0279 | Uba | Crm Implementation | John Iwoh | Abuja | Medium | Completed | 60000000 | 55000000 | 20 | 50 | 2 | 2024-12-31 | 2025-04-20 | 5000000
PRJ0280 | Nestle Nigeria | Cloud Infrastructure | Michael Dan | Abuja | Low | In Progress | 45000000 | 12000000 | 5 | 25 | 5 | 2024-04-07 |  | 33000000
PRJ0281 | Flutterwave | Erp Migration | Sarah Musa | Abuja | Low | In Progress | 25000000 | 55000000 | 20 | 0 | 2 |  |  | -30000000
PRJ0282 | Interswitch | Data Warehouse | Michael Dan | Abuja | High | Completed | 60000000 | 12000000 | 0 | 100 | 4 |  |  | 48000000
PRJ0283 | Nestle Nigeria | Network Optimization | David Bello | Lagos | High | In Progress | 15000000 | 35000000 | 20 | 50 | 2 |  |  | -20000000
PRJ0284 | Airtel | Ai Analytics Platform | Grace Adeyemi | Lagos | High | Delayed | 120000000 | 100000000 | 10 | 75 | 4 |  | 2025-02-19 | 20000000
PRJ0285 | Dangote Group | Data Warehouse | Michael Dan | Abuja | Low | Completed | 120000000 | 20000000 | 15 | 0 | 5 |  | 2024-09-10 | 100000000
PRJ0286 | Gtbank | Network Optimization | John Iwoh | Lagos | High | Completed | 60000000 | 20000000 | 10 | 90 | 2 |  | 2025-02-23 | 40000000
PRJ0287 | Airtel | Cloud Infrastructure | David Bello | Abuja | Medium | Delayed | 120000000 | 20000000 | 20 | 0 | 5 |  |  | 100000000
PRJ0288 | Uba | Mobile Banking App | David Bello | Lagos | Medium | In Progress | 15000000 | 35000000 | 15 | 90 | 4 | 2024-11-04 | 2025-01-29 | -20000000
PRJ0289 | Mtn Nigeria | Cloud Infrastructure | Michael Dan | Abuja | Medium | Delayed | 15000000 | 35000000 | 15 | 25 | 1 |  | 2024-10-21 | -20000000
PRJ0290 | Dangote Group | Network Optimization | Michael Dan | Lagos | Low | In Progress | 15000000 | 55000000 | 10 | 90 | 2 | 2024-02-16 |  | -40000000
PRJ0291 | Mtn Nigeria | Ai Analytics Platform | John Iwoh | Abuja | Low | Delayed | 15000000 | 35000000 | 20 | 50 | 3 |  | 2024-02-29 | -20000000
PRJ0292 | Mtn Nigeria | Erp Migration | Michael Dan | Abuja | High | In Progress | 120000000 | 35000000 | 0 | 25 | 1 | 2024-11-05 |  | 85000000
PRJ0293 | Access Bank | Cloud Infrastructure | David Bello | Lagos | High | Delayed | 60000000 | 100000000 | 5 | 0 | 1 | 2024-03-03 | 2024-08-25 | -40000000
PRJ0294 | Dangote Group | Cybersecurity Upgrade | Sarah Musa | Port Harcourt | Medium | In Progress | 15000000 | 55000000 | 5 | 100 | 2 | 2024-05-16 | 2024-11-09 | -40000000
PRJ0295 | Flutterwave | Mobile Banking App | Michael Dan | Abuja | High | Delayed | 60000000 | 100000000 | 20 | 100 | 2 | 2024-09-04 | 2024-11-26 | -40000000
PRJ0296 | Gtbank | Data Warehouse | John Iwoh | Abuja | Low | In Progress | 15000000 | 12000000 | 0 | 75 | 1 |  |  | 3000000
PRJ0297 | Uba | Ai Analytics Platform | Sarah Musa | Lagos | Low | Completed | 25000000 | 20000000 | 20 | 75 | 2 | 2024-02-24 | 2024-07-06 | 5000000
PRJ0298 | Dangote Group | Ai Analytics Platform | David Bello | Abuja | High | Completed | 120000000 | 100000000 | 20 | 90 | 4 |  |  | 20000000
PRJ0299 | Nestle Nigeria | Cloud Infrastructure | David Bello | Abuja | High | Completed | 120000000 | 12000000 | 5 | 90 | 3 |  |  | 108000000
PRJ0300 | Dangote Group | Network Optimization | Sarah Musa | Lagos | High | Completed | 25000000 | 12000000 | 0 | 90 | 1 | 2024-09-27 | 2024-12-27 | 13000000
PRJ0301 | Airtel | Mobile Banking App | David Bello | Port Harcourt | High | Completed | 15000000 | 55000000 | 5 | 90 | 2 |  |  | -40000000
PRJ0302 | Access Bank | Crm Implementation | Sarah Musa | Abuja | High | Completed | 45000000 | 100000000 | 5 | 50 | 3 | 2024-08-11 | 2025-01-10 | -55000000
PRJ0303 | Dangote Group | Data Warehouse | John Iwoh | Lagos | Low | Delayed | 120000000 | 100000000 | 20 | 90 | 3 |  |  | 20000000
PRJ0304 | Nestle Nigeria | Crm Implementation | Grace Adeyemi | Kano | Medium | Completed | 25000000 | 100000000 | 0 | 0 | 1 |  | 2024-07-08 | -75000000
PRJ0305 | Uba | Network Optimization | Sarah Musa | Abuja | Low | In Progress | 60000000 | 100000000 | 10 | 0 | 5 |  | 2024-07-11 | -40000000
PRJ0306 | Zenith Bank | Data Warehouse | Sarah Musa | Lagos | Low | In Progress | 25000000 | 20000000 | 5 | 25 | 3 |  |  | 5000000
PRJ0307 | Nestle Nigeria | Cybersecurity Upgrade | Sarah Musa | Lagos | Medium | Completed | 15000000 | 20000000 | 10 | 100 | 4 | 2025-02-01 | 2025-06-20 | -5000000
PRJ0308 | Access Bank | Data Warehouse | David Bello | Lagos | High | Delayed | 60000000 | 35000000 | 20 | 100 | 2 | 2024-11-08 |  | 25000000
PRJ0309 | Airtel | Network Optimization | John Iwoh | Abuja | Low | Delayed | 15000000 | 100000000 | 0 | 50 | 5 |  | 2024-10-06 | -85000000
PRJ0310 | Nestle Nigeria | Network Optimization | Sarah Musa | Lagos | Medium | In Progress | 60000000 | 12000000 | 5 | 50 | 4 |  |  | 48000000
PRJ0311 | Mtn Nigeria | Ai Analytics Platform | Sarah Musa | Abuja | High | Completed | 45000000 | 12000000 | 10 | 25 | 5 |  | 2024-05-14 | 33000000
PRJ0312 | Gtbank | Ai Analytics Platform | John Iwoh | Port Harcourt | Medium | Completed | 120000000 | 12000000 | 10 | 90 | 4 |  |  | 108000000
PRJ0313 | Dangote Group | Ai Analytics Platform | Sarah Musa | Kano | Medium | Completed | 120000000 | 55000000 | 15 | 25 | 1 |  |  | 65000000
PRJ0314 | Airtel | Data Warehouse | Sarah Musa | Port Harcourt | Low | Delayed | 120000000 | 20000000 | 15 | 50 | 4 |  |  | 100000000
PRJ0315 | Uba | Crm Implementation | John Iwoh | Kano | Low | Completed | 45000000 | 35000000 | 0 | 100 | 5 |  |  | 10000000
PRJ0316 | Dangote Group | Data Warehouse | David Bello | Lagos | Medium | In Progress | 60000000 | 35000000 | 20 | 75 | 5 |  |  | 25000000
PRJ0317 | Dangote Group | Crm Implementation | John Iwoh | Port Harcourt | Medium | Delayed | 60000000 | 35000000 | 0 | 50 | 5 | 2024-04-09 | 2024-05-09 | 25000000
PRJ0318 | Airtel | Network Optimization | David Bello | Lagos | Low | Completed | 60000000 | 100000000 | 15 | 100 | 5 | 2024-09-27 |  | -40000000
PRJ0319 | Gtbank | Network Optimization | Michael Dan | Abuja | Low | Completed | 120000000 | 35000000 | 5 | 25 | 4 | 2024-04-07 |  | 85000000
PRJ0320 | Airtel | Cloud Infrastructure | Michael Dan | Abuja | Medium | In Progress | 25000000 | 100000000 | 20 | 75 | 4 | 2024-09-01 |  | -75000000
PRJ0321 | Dangote Group | Cybersecurity Upgrade | John Iwoh | Lagos | High | Delayed | 60000000 | 35000000 | 0 | 25 | 1 | 2024-04-18 |  | 25000000
PRJ0322 | Zenith Bank | Ai Analytics Platform | Sarah Musa | Abuja | Medium | In Progress | 15000000 | 55000000 | 15 | 75 | 5 |  | 2025-01-18 | -40000000
PRJ0323 | Nestle Nigeria | Network Optimization | Sarah Musa | Abuja | High | Completed | 25000000 | 35000000 | 5 | 0 | 2 |  |  | -10000000
PRJ0324 | Zenith Bank | Network Optimization | John Iwoh | Kano | High | Completed | 15000000 | 12000000 | 20 | 50 | 1 |  | 2025-02-25 | 3000000
PRJ0325 | Zenith Bank | Data Warehouse | Grace Adeyemi | Abuja | High | In Progress | 60000000 | 20000000 | 0 | 90 | 5 | 2024-10-28 |  | 40000000
PRJ0326 | Flutterwave | Network Optimization | Sarah Musa | Kano | High | Completed | 60000000 | 20000000 | 10 | 25 | 3 | 2024-12-30 | 2025-03-20 | 40000000
PRJ0327 | Zenith Bank | Data Warehouse | Michael Dan | Abuja | High | In Progress | 15000000 | 12000000 | 10 | 100 | 4 | 2024-02-14 |  | 3000000
PRJ0328 | Uba | Mobile Banking App | Sarah Musa | Lagos | Low | In Progress | 120000000 | 12000000 | 5 | 75 | 5 | 2024-05-30 |  | 108000000
PRJ0329 | Airtel | Cybersecurity Upgrade | Grace Adeyemi | Lagos | Low | Completed | 120000000 | 100000000 | 20 | 0 | 2 |  | 2024-08-19 | 20000000
PRJ0330 | Gtbank | Crm Implementation | Michael Dan | Abuja | Medium | In Progress | 45000000 | 100000000 | 0 | 50 | 3 | 2025-01-18 |  | -55000000
PRJ0331 | Zenith Bank | Ai Analytics Platform | David Bello | Lagos | High | Delayed | 60000000 | 20000000 | 5 | 25 | 2 | 2024-09-06 | 2024-10-23 | 40000000
PRJ0332 | Uba | Crm Implementation | Sarah Musa | Kano | Medium | In Progress | 15000000 | 12000000 | 5 | 0 | 1 | 2024-02-07 |  | 3000000
PRJ0333 | Nestle Nigeria | Cloud Infrastructure | Michael Dan | Port Harcourt | High | Completed | 60000000 | 12000000 | 15 | 25 | 2 | 2024-02-20 | 2024-07-18 | 48000000
PRJ0334 | Zenith Bank | Erp Migration | Michael Dan | Abuja | Low | Delayed | 120000000 | 100000000 | 20 | 100 | 3 |  | 2024-09-08 | 20000000
PRJ0335 | Access Bank | Data Warehouse | Grace Adeyemi | Abuja | Medium | Completed | 45000000 | 55000000 | 10 | 90 | 5 |  |  | -10000000
PRJ0336 | Uba | Cybersecurity Upgrade | Sarah Musa | Kano | High | Delayed | 15000000 | 35000000 | 5 | 25 | 4 |  |  | -20000000
PRJ0337 | Uba | Erp Migration | Grace Adeyemi | Lagos | Medium | Completed | 60000000 | 12000000 | 0 | 0 | 1 | 2024-07-08 |  | 48000000
PRJ0338 | Gtbank | Mobile Banking App | Michael Dan | Abuja | Medium | In Progress | 15000000 | 35000000 | 10 | 50 | 5 |  |  | -20000000
PRJ0339 | Flutterwave | Crm Implementation | David Bello | Lagos | Low | Delayed | 15000000 | 55000000 | 0 | 90 | 3 |  |  | -40000000
PRJ0340 | Uba | Erp Migration | John Iwoh | Abuja | Medium | Delayed | 60000000 | 12000000 | 5 | 75 | 5 | 2024-11-06 |  | 48000000
PRJ0341 | Interswitch | Cloud Infrastructure | David Bello | Abuja | High | Delayed | 120000000 | 12000000 | 10 | 75 | 2 |  |  | 108000000
PRJ0342 | Zenith Bank | Data Warehouse | Michael Dan | Lagos | Medium | Completed | 45000000 | 100000000 | 0 | 90 | 3 |  |  | -55000000
PRJ0343 | Airtel | Cybersecurity Upgrade | David Bello | Lagos | Low | Delayed | 60000000 | 55000000 | 20 | 25 | 5 |  |  | 5000000
PRJ0344 | Zenith Bank | Cybersecurity Upgrade | Michael Dan | Abuja | Medium | In Progress | 45000000 | 12000000 | 15 | 75 | 4 | 2024-05-16 |  | 33000000
PRJ0345 | Zenith Bank | Erp Migration | Sarah Musa | Abuja | Medium | Delayed | 25000000 | 55000000 | 15 | 0 | 1 | 2024-02-03 |  | -30000000
PRJ0346 | Airtel | Ai Analytics Platform | Grace Adeyemi | Lagos | Low | In Progress | 25000000 | 55000000 | 20 | 75 | 1 | 2024-01-20 |  | -30000000
PRJ0347 | Interswitch | Data Warehouse | Michael Dan | Lagos | High | Delayed | 25000000 | 12000000 | 15 | 75 | 1 |  |  | 13000000
PRJ0348 | Airtel | Ai Analytics Platform | David Bello | Port Harcourt | High | In Progress | 120000000 | 100000000 | 0 | 100 | 1 |  |  | 20000000
PRJ0349 | Nestle Nigeria | Network Optimization | David Bello | Lagos | Medium | In Progress | 60000000 | 20000000 | 0 | 100 | 3 |  |  | 40000000
PRJ0350 | Gtbank | Data Warehouse | David Bello | Lagos | Low | Delayed | 25000000 | 35000000 | 10 | 50 | 2 |  |  | -10000000
PRJ0351 | Dangote Group | Ai Analytics Platform | Michael Dan | Lagos | High | Delayed | 25000000 | 12000000 | 20 | 90 | 1 | 2024-01-19 |  | 13000000
PRJ0352 | Airtel | Ai Analytics Platform | John Iwoh | Kano | Medium | Delayed | 60000000 | 12000000 | 20 | 50 | 4 |  |  | 48000000
PRJ0353 | Nestle Nigeria | Crm Implementation | Grace Adeyemi | Port Harcourt | Low | Completed | 15000000 | 20000000 | 10 | 100 | 5 |  |  | -5000000
PRJ0354 | Dangote Group | Cybersecurity Upgrade | Michael Dan | Port Harcourt | Low | Completed | 45000000 | 100000000 | 15 | 75 | 1 |  |  | -55000000
PRJ0355 | Interswitch | Cloud Infrastructure | John Iwoh | Kano | High | Delayed | 120000000 | 20000000 | 15 | 90 | 1 | 2024-10-31 | 2024-12-31 | 100000000
PRJ0356 | Mtn Nigeria | Cybersecurity Upgrade | John Iwoh | Lagos | High | Delayed | 25000000 | 55000000 | 0 | 100 | 2 |  |  | -30000000
PRJ0357 | Interswitch | Data Warehouse | John Iwoh | Lagos | Medium | In Progress | 60000000 | 20000000 | 20 | 90 | 3 |  |  | 40000000
PRJ0358 | Nestle Nigeria | Data Warehouse | Sarah Musa | Kano | High | Delayed | 120000000 | 55000000 | 15 | 50 | 2 |  |  | 65000000
PRJ0359 | Interswitch | Ai Analytics Platform | Sarah Musa | Lagos | Medium | In Progress | 45000000 | 35000000 | 0 | 90 | 4 |  | 2024-02-13 | 10000000
PRJ0360 | Access Bank | Cloud Infrastructure | John Iwoh | Kano | High | In Progress | 120000000 | 100000000 | 20 | 0 | 5 |  |  | 20000000
PRJ0361 | Flutterwave | Data Warehouse | Michael Dan | Kano | Medium | Completed | 15000000 | 100000000 | 5 | 0 | 4 |  | 2025-03-01 | -85000000
PRJ0362 | Nestle Nigeria | Cybersecurity Upgrade | John Iwoh | Port Harcourt | High | Completed | 25000000 | 20000000 | 0 | 100 | 2 |  |  | 5000000
PRJ0363 | Dangote Group | Cloud Infrastructure | Sarah Musa | Kano | Low | Delayed | 15000000 | 35000000 | 20 | 75 | 2 |  |  | -20000000
PRJ0364 | Nestle Nigeria | Erp Migration | Michael Dan | Port Harcourt | Medium | In Progress | 120000000 | 20000000 | 10 | 100 | 3 |  | 2024-11-04 | 100000000
PRJ0365 | Zenith Bank | Cybersecurity Upgrade | John Iwoh | Kano | High | Completed | 25000000 | 12000000 | 5 | 90 | 4 | 2024-11-04 | 2024-12-08 | 13000000
PRJ0366 | Mtn Nigeria | Cloud Infrastructure | Michael Dan | Abuja | High | Completed | 15000000 | 12000000 | 0 | 50 | 5 |  | 2025-05-28 | 3000000
PRJ0367 | Uba | Cybersecurity Upgrade | John Iwoh | Kano | High | Completed | 120000000 | 20000000 | 10 | 100 | 3 |  |  | 100000000
PRJ0368 | Dangote Group | Mobile Banking App | Michael Dan | Kano | High | Completed | 15000000 | 20000000 | 15 | 0 | 1 |  | 2025-02-01 | -5000000
PRJ0369 | Access Bank | Data Warehouse | Grace Adeyemi | Abuja | High | Completed | 60000000 | 20000000 | 0 | 25 | 3 |  |  | 40000000
PRJ0370 | Interswitch | Cloud Infrastructure | David Bello | Abuja | Medium | In Progress | 60000000 | 35000000 | 5 | 90 | 4 |  |  | 25000000
PRJ0371 | Dangote Group | Ai Analytics Platform | David Bello | Lagos | Low | In Progress | 25000000 | 100000000 | 0 | 25 | 4 |  | 2024-05-26 | -75000000
PRJ0372 | Access Bank | Cloud Infrastructure | Michael Dan | Abuja | Medium | Completed | 60000000 | 35000000 | 10 | 75 | 4 |  | 2024-04-01 | 25000000
PRJ0373 | Airtel | Network Optimization | Grace Adeyemi | Abuja | Medium | In Progress | 25000000 | 20000000 | 5 | 0 | 4 |  |  | 5000000
PRJ0374 | Nestle Nigeria | Cybersecurity Upgrade | Sarah Musa | Kano | Low | Delayed | 45000000 | 100000000 | 20 | 0 | 5 | 2024-02-07 |  | -55000000
PRJ0375 | Flutterwave | Cybersecurity Upgrade | Sarah Musa | Port Harcourt | Medium | Delayed | 25000000 | 100000000 | 15 | 0 | 2 |  | 2024-10-25 | -75000000
PRJ0376 | Mtn Nigeria | Crm Implementation | John Iwoh | Abuja | Medium | Completed | 45000000 | 55000000 | 5 | 0 | 2 |  |  | -10000000
PRJ0377 | Zenith Bank | Network Optimization | John Iwoh | Kano | Medium | In Progress | 15000000 | 20000000 | 15 | 25 | 5 |  |  | -5000000
PRJ0378 | Nestle Nigeria | Cybersecurity Upgrade | Grace Adeyemi | Kano | Medium | In Progress | 45000000 | 55000000 | 15 | 25 | 5 | 2024-05-25 |  | -10000000
PRJ0379 | Gtbank | Cloud Infrastructure | Grace Adeyemi | Abuja | Medium | Delayed | 15000000 | 55000000 | 10 | 75 | 3 |  |  | -40000000
PRJ0380 | Flutterwave | Data Warehouse | John Iwoh | Abuja | High | In Progress | 120000000 | 100000000 | 10 | 90 | 3 |  |  | 20000000
PRJ0381 | Gtbank | Cybersecurity Upgrade | Michael Dan | Kano | Medium | Completed | 60000000 | 55000000 | 15 | 50 | 4 |  |  | 5000000
PRJ0382 | Access Bank | Data Warehouse | David Bello | Port Harcourt | Medium | In Progress | 120000000 | 35000000 | 5 | 50 | 2 | 2024-01-28 |  | 85000000
PRJ0383 | Airtel | Ai Analytics Platform | David Bello | Port Harcourt | Medium | Completed | 15000000 | 100000000 | 15 | 25 | 4 |  |  | -85000000
PRJ0384 | Mtn Nigeria | Network Optimization | Michael Dan | Abuja | Medium | Delayed | 15000000 | 55000000 | 15 | 25 | 5 | 2024-06-04 |  | -40000000
PRJ0385 | Uba | Cloud Infrastructure | Grace Adeyemi | Abuja | Medium | In Progress | 120000000 | 100000000 | 10 | 90 | 2 | 2024-10-28 | 2025-01-16 | 20000000
PRJ0386 | Airtel | Cybersecurity Upgrade | Michael Dan | Abuja | Low | In Progress | 120000000 | 12000000 | 20 | 50 | 4 |  |  | 108000000
PRJ0387 | Nestle Nigeria | Network Optimization | Sarah Musa | Abuja | Low | Completed | 60000000 | 100000000 | 20 | 0 | 2 | 2024-04-07 |  | -40000000
PRJ0388 | Mtn Nigeria | Crm Implementation | John Iwoh | Lagos | High | Delayed | 25000000 | 12000000 | 15 | 50 | 5 |  | 2024-07-02 | 13000000
PRJ0389 | Flutterwave | Erp Migration | Grace Adeyemi | Lagos | High | Delayed | 120000000 | 20000000 | 5 | 25 | 3 |  | 2024-10-04 | 100000000
PRJ0390 | Zenith Bank | Network Optimization | John Iwoh | Abuja | Low | Completed | 45000000 | 55000000 | 15 | 100 | 1 |  |  | -10000000
PRJ0391 | Airtel | Network Optimization | Grace Adeyemi | Abuja | High | In Progress | 25000000 | 55000000 | 0 | 0 | 3 | 2024-03-19 | 2024-04-28 | -30000000
PRJ0392 | Zenith Bank | Ai Analytics Platform | David Bello | Port Harcourt | Medium | In Progress | 60000000 | 20000000 | 5 | 0 | 5 |  |  | 40000000
PRJ0393 | Dangote Group | Network Optimization | John Iwoh | Lagos | High | Completed | 120000000 | 100000000 | 20 | 75 | 4 |  |  | 20000000
PRJ0394 | Interswitch | Cloud Infrastructure | Grace Adeyemi | Lagos | Medium | Completed | 45000000 | 35000000 | 20 | 0 | 3 |  |  | 10000000
PRJ0395 | Zenith Bank | Network Optimization | David Bello | Abuja | High | Delayed | 45000000 | 20000000 | 5 | 0 | 3 |  |  | 25000000
PRJ0396 | Access Bank | Data Warehouse | Michael Dan | Lagos | High | Completed | 60000000 | 100000000 | 5 | 100 | 3 |  | 2025-02-15 | -40000000
PRJ0397 | Airtel | Cloud Infrastructure | Sarah Musa | Lagos | High | In Progress | 60000000 | 55000000 | 5 | 75 | 5 | 2025-01-08 |  | 5000000
PRJ0398 | Uba | Cybersecurity Upgrade | David Bello | Abuja | High | In Progress | 15000000 | 12000000 | 20 | 50 | 4 | 2024-08-17 | 2024-10-06 | 3000000
PRJ0399 | Mtn Nigeria | Data Warehouse | John Iwoh | Abuja | High | Completed | 25000000 | 35000000 | 0 | 100 | 2 |  |  | -10000000
PRJ0400 | Flutterwave | Data Warehouse | Michael Dan | Abuja | High | In Progress | 45000000 | 100000000 | 0 | 75 | 2 | 2024-01-05 |  | -55000000